## Slide 1: MS Project 2013 Level I Introduction
http://www.profburnett.com

## Slide 2: Outline
Introductions
Class Outline
Review Class Website

## Slide 3: Instructor Info
Carl Burnett
Instructor with MCC since 2007
Also teaches at JHU & CTC
Military 22 Years – Corps of Engineers
IT Contractor 20 Years (BAH, GD, Independent)
profburnett@live.com
carl.burnett@montgomerycollege.edu
240.696.1906

## Slide 4: Introductions
Name
Job
What do you to expect from course?

## Slide 5: Class Website
Class Website
Download Class Files
Bring in a Project to Manage

## Slide 6: Course Outline
Day 1
  Lesson 1 - Overview of Project Management & MS Project
  Lesson 2 - Starting a new project plan
  Lesson 3 - Building a task list
  Lesson 4 - Setting up resources
Day 2
  Lesson 5 - Assigning resources to tasks
  Lesson 6 - Formatting and sharing your plan
  Lesson 7 - Tracking progress
  Lesson 8 - Project Management Toolkit

## Slide 7: Day 1
  Lesson 1 - Overview of Project Management & MS Project
  Lesson 2 - Starting a new project plan
  Lesson 3 - Building a task list
  Lesson 4 - Setting up resources

## Slide 8: The Project Management Process

## Slide 9: Definition of a Project
“A project is a sequence of unique, complex, and connected activities having one goal or purpose and that must be completed by a specific time, within budget, and according to specifications.”

## Slide 10: Activities
An activity is a chunk of work
Activities are completed in sequence
  Sequence determined by technical requirements
  Think in terms of inputs and outputs
Characteristics of project activities
  Unique
  Complex
  Connected

## Slide 11: Characteristics of Projects
One goal
Specified Time
Within Budget
According to specification – Customer’s requirements

## Slide 12: Project Parameters
Scope:
  Defines the boundaries of the project
  What will be done in the project
  What will NOT be done
  Functional Specification
  Statement of Work
Quality
  Product quality - quality of project product
  Process quality - how well project managed

## Slide 13: Project Parameters (cont.)
Cost:
  Estimate at first
  Refined throughout
Time
  Inverse relationship to cost
  Future Time:
Resources
  People
  Equipment
  Physical facilities
  Supplies
  Fixed or variable
  Most impact on the schedule

## Slide 14: The Scope Triangle
Resource Availability
Cost
Time
Scope

## Slide 15: Creeps
Scope creep – Change in project
Hope creep – Project team member is behind schedule
Effort creep – Work not contributing to project progress
Feature creep – Adding features and functions to project product

## Slide 16: Lesson 2: Starting a new project plan

## Slide 17: Lesson 3: Building a task list
Topic A: Creating a task list
  A-1: Exploring user-controlled scheduling
  A-2: Adding tasks and durations in auto schedule mode
  A-3: Changing the scheduling mode for all new files
Topic B: Modifying a task list
  B-1: Inserting and deleting tasks
  B-2: Rearranging tasks
  B-3: Formatting the task list
Topic C: The Work Breakdown Structure
  C-1: Creating a project summary task
  C-2: Defining a Work Breakdown Structure
  C-3: Setting milestones
  C-4: Applying Gantt Chart styles

## Slide 18: Work Breakdown Structure
“A hierarchical description of the work that must be done to complete the project as defined in the Project Overview Statement.”
Inputs
  Project Charter (POS)
  Requirements Document
Terms
  Activity: Chunk of work
  Tasks: Smaller chunk of work. Activities are made up of tasks
  Work Package: Complete description of how the tasks that make up the activity will actually be done

## Slide 19: Work Breakdown Structure
Charter
Work Breakdown Schedule (WBS)
Project Requirement Document (PRD)
Activity
Work Pak
Dictionary
PRTM
RAM
Estimate
Network Chart
Phases
A B C D

## Slide 20: Work Breakdown Structure (WBS)
Work Breakdown Chart
Work Pack Breakdown
Task Number Identification Scheme
  1.0
  1.1
  1.1.1
  A
  A.a
  A.a.(a)

## Slide 21: Decomposition
The process of breaking down work into a hierarchy of activities, tasks, and work packages
Uses
Estimate Duration
Determine Resources
Schedule Work
Level # 0
Level # 1
Level # 2
Level # n
Goal
Activity
Activity
Activity
Activity
Activity
Activity
Activity
Task # 1
Task #2
Task # 3
Task # n
Work Package

## Slide 22: Uses for the WBS
Thought Process Tool
Architectural Design Tool
Planning Tool
Project Status Reporting Tool

## Slide 23: Generating the WBS
Top-Down Approach: Start with goal and continue to partition work until it has been sufficiently defined
  Team Approach Variation
  Subteam Approach Variation
Bottom-Up Approach: First-level tasks are identified. Then groups are formed around first-level tasks where these groups brainstorm the activities needed to complete the first-level task.

## Slide 24: Six Criteria to Test for WBS Completeness
Status/Completion is measurable
The activity is bounded
The activity has a deliverable
Time and cost are easily estimated
Activity duration is within acceptable limits
Work assignments are independent
Seventh Criteria – Project manager’s judgment that the WBS is not complete

## Slide 25: Exceptions to the Completion Criteria Rule
Stopping Before Completion Criteria Are Met
Decomposing Beyond Completion of the Criteria

## Slide 26: Approaches to Building the WBS
Noun-type: In terms of the components of the deliverable
  Physical Decomposition
  Functional Decomposition
Verb-type: In terms of the actions that must be done to produce the deliverable
  Design-build-test-implement
  Objectives
Organizational: In terms of the units that will create the deliverable
  Geographic
  Departmental
  Business Process

## Slide 27: Representing WBS Tree Structure
My Training Manual
1 Start Book
2 Research Phase
3 Outline Phase
4 Development Phase
5 Edit Phase
6 Review Phase
7 Print Phase
8 Book Complete
1- Investigate the Software
2 - Search the Web
3 - Interview Subject Matter Experts
1 - Create Outline
2 - Present to Publisher
3 - Review with Subject Matter Expert
4 - Revise Outline
1 - Write Lessons 1-5
2 - Write Lessons 6-10
3 - Add Graphics
1 - Check Grammar, Spelling, and Proofread
2 - Check for Technical Accuracy
1 - Approve Editing Changes
2 - Meet with Editor
1 - Print Proof
2 - Review Proof
3 - Print Final

## Slide 28: Representing WBS Indented Outline
Activity Sub-Task Activity / Task
Task No
My Training Manual
1 Start Book
2 Research Phase
1 Investigate the Software
2 Search the Web
3 Interview Subject Matter Experts
3 Outline Phase
1 Create Outline
2 Present to Publisher
3 Review with Subject Matter Expert
4 Revise Outline
4 Development Phase
1 Write Lessons 1-5
2 Write Lessons 6-10
3 Add Graphics
Activity Sub-Task Activity / Task
Task No
5 Edit Phase
1 Check Grammar, Spelling, and Proofread
2 Check for Technical Accuracy
6 Review Phase
1 Approve Editing Changes
2 Meet with Editor
7 Print Phase
1 Print Proof
2 Review Proof
3 Print Final
8 Book Complete

## Slide 29: Representing WBS Waterfall Structure
Activity / Task No | Activity / Task
 | My Training Manual
1 | Start Book
2 | Research Phase
2.1 | Investigate the Software
2.2 | Search the Web
2.3 | Interview Subject Matter Experts
3 | Outline Phase
3.1 | Create Outline
3.2 | Present to Publisher
3.3 | Review with Subject Matter Expert
3.4 | Revise Outline
4 | Development Phase
4.1 | Write Lessons 1-5
4.2 | Write Lessons 6-10
4.3 | Add Graphics
5 | Edit Phase
5.1 | Check Grammar, Spelling, and Proofread
5.2 | Check for Technical Accuracy
6 | Review Phase
6.1 | Approve Editing Changes
6.2 | Meet with Editor
7 | Print Phase
7.1 | Print Proof
7.2 | Review Proof
7.3 | Print Final
8 | Book Complete

## Slide 30: Task Duration Estimates
E = Estimated Duration
M = The Most Probable Time
O = The Most Optimistic Time (5% Probability)
P = The Most Pessimistic Time (5% Probability)

## Slide 31: Units
Percentage of a resource’s time
Resource working half-time on task

## Slide 32: WBS
Task No | WBS | Task | Most Optimistic | Most Probable | Most Pessimistic | Est Duration | Task Duration
0 |  | My Training Manual |  |  |  |  | 
1 | 1 | Start Book |  |  |  |  | 
2 | 2 | Research Phase |  |  |  |  | 
3 | 2.1 | Investigate the Software | 4 | 5 | 6 | 5 | 5
4 | 2.2 | Search the Web | 1 | 1 | 1 | 1 | 1
5 | 2.3 | Interview Subject Matter Experts | 1 | 2 | 3 | 2 | 2
6 | 3 | Outline Phase |  |  |  |  | 
7 | 3.1 | Create Outline | 2 | 3 | 4 | 3 | 3
8 | 3.2 | Present to Publisher | 1 | 1 | 1 | 1 | 1
9 | 3.3 | Review with Subject Matter Expert | 1 | 1 | 1 | 1 | 1
10 | 3.4 | Revise Outline | 1 | 1 | 1 | 1 | 1
11 | 4 | Development Phase |  |  |  |  | 
12 | 4.1 | Write Lessons 1-5 | 20 | 25 | 30 | 25 | 25
13 | 4.2 | Write Lessons 6-10 | 10 | 12 | 17 | 12.5 | 12.5
14 | 4.3 | Add Graphics | 1 | 1 | 4 | 1.5 | 1.54
15 | 5 | Edit Phase |  |  |  |  | 
16 | 5.1 | Check Grammar, Spelling, and Proofread | 1 | 1 | 4 | 1.5 | 1.5
17 | 5.2 | Check for Technical Accuracy | 1 | 1 | 1 | 1 | 1
18 | 6 | Review Phase |  |  |  |  | 
19 | 6.1 | Approve Editing Changes | 1 | 1 | 1 | 1 | 1
20 | 6.2 | Meet with Editor | 1 | 1 | 1 | 1 | 1
21 | 7 | Print Phase |  |  |  |  | 
22 | 7.1 | Print Proof | 1 | 1 | 1 | 1 | 1
23 | 7.2 | Review Proof | 1 | 1 | 1 | 1 | 1
24 | 7.3 | Print Final | 1 | 1 | 1 | 1 | 1
25 | 8 | Book Complete |  |  |  |  | 

## Slide 33: Task Relationships
Finish-to-Start (FS)
Start-to-Start (SS)
Finish-to-Finish (FF)
Start-to-Finish (SF)

## Slide 34
Lesson 4 - Setting up resources

## Slide 35: Day 1 - Review
  Lesson 1 - Overview of Project Management & MS Project
  Lesson 2 - Starting a new project plan
  Lesson 3 - Building a task list
  Lesson 4 - Setting up resources

## Slide 36: Day 2
Lesson 5 - Assigning resources to tasks
Lesson 6 - Formatting and sharing your plan
Lesson 7 - Tracking progress
Lesson 8 - Project Management Toolkit

## Slide 37: Lesson 5: Assigning resources to tasks

## Slide 38: Lesson 6: Formatting and sharing your plan

## Slide 39: Lesson 7 - Tracking progress

## Slide 40: Lesson 8 - Project Management Toolkit

## Slide 41: Day 2 - Review
Lesson 5 - Assigning resources to tasks
Lesson 6 - Formatting and sharing your plan
Lesson 7 - Tracking progress
Lesson 8 - Project Management Toolkit

## Slide 42: Class Evaluation
WD&CE Course Evaluation Form
http://webdb.montgomerycollege.edu/internet/wdceevals/wdceevals.cfm
Course Name: MS Project 2013 – Level I
Course CRN: 35510
Course Start Date: April 5, 2016
Course Instructor: Carl Burnett