## Slide 1: Monitoring and Reporting Project Progress
http://www.profburnett.com

## Slide 2: Outline
Control versus Risk
Control versus Quality
Progress Reporting System
Applying Graphical Reporting Tools
Deciding on Report Level of Detail
Managing Project Status Meetings
Managing Change
Change Control and the Project Life Cycles
Managing Problem Escalation

## Slide 3: Control versus Risk
Controls: “Actions taken as a result of reports.”
Purpose of Controls
  To track progress
  To detect variance from plan
  To take corrective action
High Control – Low Risk
Low Control – High Risk

## Slide 4: Balancing the Control System
Point of Diminishing Returns
Excessive Control Can Limit Creativity
Excessive Control Can Increase Reporting Overhead
$
Control
Risk
Total Cost

## Slide 5: Control versus Quality
Positive Correlation between Control and Quality

## Slide 6: Progress Reporting System
Characteristics of a good reporting system
  Timely, complete, and accurate status information
  Minimizes overhead needed for reporting
  Readily acceptable to project team and senior management
  Early warning of pending problems
  Easily understood
Types of Project Status Reports
  Current Period Reports
  Cumulative Reports
  Exception Reports
  Stoplight Reports
  Variance Reports

## Slide 7: Variance Reports
Report has three columns
  The planned number
  The actual number
  The difference between the two numbers
Report can be numeric or graphical
Five Reasons to report on duration and cost variances
  Catch deviations from the curve early
  Dampen oscillation
  Allow early corrective action
  Determine weekly schedule variance
  Determine weekly effort (person hours/days) variance

## Slide 8: How and What Information to Update
Determine a set period of time and day of week
Report actual work accomplished during this period
Report start and finish dates
Record days of duration accomplished and remaining
Report resource effort (hours/day) spent and remaining (in-progress work only)
Report percent complete
Frequency of gathering and reporting project progress
  Typically weekly but can be more or less frequent depending on the project

## Slide 9: Variances
Positive
  Indicates ahead of schedule or less cost than planned
  May not always be good
Negative
  Indicates behind schedule or more cost than planned
  May not always be bad

## Slide 10: Gantt Charts

## Slide 11: Milestone Trend Charts
Successive Slippages
On Schedule
3
2
1
3
2
1
Late
Early








Notes: 

## Slide 12: Milestone Trend Charts
Radical Change
On Schedule
3
2
1
3
2
1
Late
Early







## Slide 13: Milestone Trend Charts
Schedule Shift
On Schedule
3
2
1
3
2
1
Late
Early







## Slide 14: Milestone Trend Charts
Successive Runs
On Schedule
3
2
1
3
2
1
Late
Early









## Slide 15: Earned Value Analysis
Measures project performance in dollar values
Progress
Time
Baseline
Cost Variance
Update Date
Actual
Progress
Time
Baseline
Cost Variance
Update Date
Actual
Schedule Variance

## Slide 16: Earned Value Analysis (Cont.)

## Slide 17: Earned Value Analysis (Cont.)
Progress
Time
Schedule Variance
Update Date
AC
PV
EV
Cost Variance
Progress
Time
Estimate to Complete
Update Date
AC
PV
EV
Baseline
Finish
Date

## Slide 18: Earned Value Analysis (Cont.)
Schedule Performance Index
  SPI = EV / PV
Cost Performance Index
  CPI = EV / AC

## Slide 19: Deciding on the Report Level of Detail
Activity Manager
  Most detailed and granular information
Project Manager
  Most detailed and granular information
  Emphasis on schedule and budget
Senior Management
  Graphical
  Milestone-level or summary-level

## Slide 20: Managing Project Status Meetings
Who should attend?
  Determine if some attendees just need information and that the meeting minutes will suffice
  If two or more members need to discuss a tangential issue, then consider using a sidebar meeting
When are they held?
  Weekly
  On a regular basis
What is their purpose?
  To encourage the free flow of information
Format
  Top-down (project champion, customer, project manager, and so on)
  Record minutes

## Slide 21: Managing Change
Two essential documents to the change management process
  Project Change Request
  Project Impact Statement
Six possible outcomes from a change request
  It can be accommodated within the project resources and timelines
  It can be accommodated but will require an extension of the deliverable schedule
  It can be accommodated within the current deliverable schedule, but additional resources will be needed
  It can be accommodated, but additional resources and an extension of the deliverable schedule will be required
  It can be accommodated with a multiple release strategy and prioritizing of the deliverables across the release date
  It cannot be accommodated without a significant change to the project

## Slide 22: A Typical Change Control Process

## Slide 23: Change Control Form

## Slide 24: Change Control and Project Management Approaches
Linear Approaches
  Most resistant to change
  Too many change requests can severely impact the project
Incremental Approaches
  Can handle some change between increments
Iterative Approaches
  Better designed to handle change requests
  Schedule and budget contingencies to handle change
Adaptive Approaches
  Change is required in this approach as the way to refine customer expectations
Extreme Approaches
  Built on constant change

## Slide 25: Managing Problem Escalation
Project manager-based strategies
  Non-critical path: use free float
  Schedule compression
  Reassign resources
Resource manager-based strategies
  Ask for additional resources
  Shift resources from later in the project to current needs
Customer-based strategies
  Consider multiple-release strategies
  Ask for a time extension

## Slide 26: Problem Management Meetings
Provide an oversight function to identify, monitor, and resolve problems
Problem is identified in status meeting
Ad-hoc group is formed to handle problem
Progress reports are presented at problem status meetings
Group is disbanded once problem is resolved
Solution is documented

## Slide 27: Review
Control versus Risk
Control versus Quality
Progress Reporting System
Applying Graphical Reporting Tools
Deciding on Report Level of Detail
Managing Project Status Meetings
Managing Change
Change Control and the Project Life Cycles
Managing Problem Escalation