## Slide 1: MS Project 2016 Level I
http://www.profburnett.com

## Slide 2: Outline
Introductions
Class Outline
Review Class Website

## Slide 3: Instructor Info
Carl Burnett
Instructor with MCC since 2007
Military – Corps of Engineers
IT Contractor - BAH, GD, Independent
profburnett@live.com
carl.burnett@montgomerycollege.edu
240.696.1906

## Slide 4: Introductions
Name
Job
What do you to expect from course?

## Slide 5: Class Website
Class Website
Download Class Files
Bring in a Project to Manage

## Slide 6: Course Outline
Session I
  Lesson 1 - Overview of Project Management & MS Project
  Lesson 2 - Starting a new project plan
  Lesson 3 - Building a task list
  Lesson 4 - Setting up resources
Session II
  Lesson 5 - Assigning resources to tasks
  Lesson 6 - Formatting and sharing your plan
  Lesson 7 - Tracking progress
  Lesson 8 - Project Management Toolkit

## Slide 7: Session I
  Lesson 1 - Overview of Project Management & MS Project
  Lesson 2 - Starting a new project plan
  Lesson 3 - Building a task list
  Lesson 4 - Setting up resources

## Slide 8: The Project Management Process

## Slide 9: Definition of a Project
“A project is a sequence of unique, complex, and connected activities having one goal or purpose and that must be completed by a specific time, within budget, and according to specifications.”

## Slide 10: Activities
An activity is a chunk of work
Activities are completed in sequence
  Sequence determined by technical requirements
  Think in terms of inputs and outputs
Characteristics of project activities
  Unique
  Complex
  Connected

## Slide 11: Characteristics of Projects
One goal
Specified Time
Within Budget
According to specification – Customer’s requirements

## Slide 12: Project Parameters
Scope:
  Defines the boundaries of the project
  What will be done in the project
  What will NOT be done
  Functional Specification
  Statement of Work
Quality
  Product quality - quality of project product
  Process quality - how well project managed

## Slide 13: Project Parameters (cont.)
Cost:
  Estimate at first
  Refined throughout
Time
  Inverse relationship to cost
  Future Time:
Resources
  People
  Equipment
  Physical facilities
  Supplies
  Fixed or variable
  Most impact on the schedule

## Slide 14: The Scope Triangle
Resource Availability
Cost
Time
Scope

## Slide 15: Creeps
Scope creep – Change in project
Hope creep – Project team member is behind schedule
Effort creep – Work not contributing to project progress
Feature creep – Adding features and functions to project product

## Slide 16: MS Project 2016
MS Project 2016 Plans

## Slide 17: Lesson 2: Starting a new project plan
Create New Plan
Set Start Date
Set Nonworking Days
Enter Plan Details
Student Exercise – Page 45

## Slide 18: Lesson 3: Building a task list
The Work Breakdown Structure
Creating a task list
Enter Task Durations and Dates
Enter Milestones
  Creating a project summary task
  Link Tasks to Create Dependencies
  Manual and Automatic Scheduling
  Plan Duration and Finish Date
  Task Information
  Student Exercise – Page 70

## Slide 19: Work Breakdown Structure
“A hierarchical description of the work that must be done to complete the project as defined in the Project Overview Statement.”
Inputs
  Project Charter (POS)
  Requirements Document
Terms
  Activity: Chunk of work
  Tasks: Smaller chunk of work. Activities are made up of tasks
  Work Package: Complete description of how the tasks that make up the activity will actually be done

## Slide 20: Work Breakdown Structure
Charter
Work Breakdown Schedule (WBS)
Project Requirement Document (PRD)
Activity
Work Pak
Dictionary
PRTM
RAM
Estimate
Network Chart
Phases
A B C D

## Slide 21: Work Breakdown Structure (WBS)
Work Breakdown Chart
Work Pack Breakdown
Task Number Identification Scheme
  1.0
  1.1
  1.1.1
  A
  A.a
  A.a.(a)

## Slide 22: Decomposition
The process of breaking down work into a hierarchy of activities, tasks, and work packages
Uses
Estimate Duration
Determine Resources
Schedule Work
Level # 0
Level # 1
Level # 2
Level # n
Goal
Activity
Activity
Activity
Activity
Activity
Activity
Activity
Task # 1
Task #2
Task # 3
Task # n
Work Package

## Slide 23: Uses for the WBS
Thought Process Tool
Architectural Design Tool
Planning Tool
Project Status Reporting Tool

## Slide 24: Generating the WBS
Top-Down Approach: Start with goal and continue to partition work until it has been sufficiently defined
  Team Approach Variation
  Subteam Approach Variation
Bottom-Up Approach: First-level tasks are identified. Then groups are formed around first-level tasks where these groups brainstorm the activities needed to complete the first-level task.

## Slide 25: Six Criteria to Test for WBS Completeness
Status/Completion is measurable
The activity is bounded
The activity has a deliverable
Time and cost are easily estimated
Activity duration is within acceptable limits
Work assignments are independent
Seventh Criteria – Project manager’s judgment that the WBS is not complete

## Slide 26: Exceptions to the Completion Criteria Rule
Stopping Before Completion Criteria Are Met
Decomposing Beyond Completion of the Criteria

## Slide 27: Approaches to Building the WBS
Noun-type: In terms of the components of the deliverable
  Physical Decomposition
  Functional Decomposition
Verb-type: In terms of the actions that must be done to produce the deliverable
  Design-build-test-implement
  Objectives
Organizational: In terms of the units that will create the deliverable
  Geographic
  Departmental
  Business Process

## Slide 28: Representing WBS Tree Structure
My Training Manual
1 Start Book
2 Research Phase
3 Outline Phase
4 Development Phase
5 Edit Phase
6 Review Phase
7 Print Phase
8 Book Complete
1- Investigate the Software
2 - Search the Web
3 - Interview Subject Matter Experts
1 - Create Outline
2 - Present to Publisher
3 - Review with Subject Matter Expert
4 - Revise Outline
1 - Write Lessons 1-5
2 - Write Lessons 6-10
3 - Add Graphics
1 - Check Grammar, Spelling, and Proofread
2 - Check for Technical Accuracy
1 - Approve Editing Changes
2 - Meet with Editor
1 - Print Proof
2 - Review Proof
3 - Print Final

## Slide 29: Representing WBS Indented Outline
Activity Sub-Task Activity / Task
Task No
My Training Manual
1 Start Book
2 Research Phase
1 Investigate the Software
2 Search the Web
3 Interview Subject Matter Experts
3 Outline Phase
1 Create Outline
2 Present to Publisher
3 Review with Subject Matter Expert
4 Revise Outline
4 Development Phase
1 Write Lessons 1-5
2 Write Lessons 6-10
3 Add Graphics
Activity Sub-Task Activity / Task
Task No
5 Edit Phase
1 Check Grammar, Spelling, and Proofread
2 Check for Technical Accuracy
6 Review Phase
1 Approve Editing Changes
2 Meet with Editor
7 Print Phase
1 Print Proof
2 Review Proof
3 Print Final
8 Book Complete

## Slide 30: Representing WBS Waterfall Structure
Activity / Task No | Activity / Task
 | My Training Manual
1 | Start Book
2 | Research Phase
2.1 | Investigate the Software
2.2 | Search the Web
2.3 | Interview Subject Matter Experts
3 | Outline Phase
3.1 | Create Outline
3.2 | Present to Publisher
3.3 | Review with Subject Matter Expert
3.4 | Revise Outline
4 | Development Phase
4.1 | Write Lessons 1-5
4.2 | Write Lessons 6-10
4.3 | Add Graphics
5 | Edit Phase
5.1 | Check Grammar, Spelling, and Proofread
5.2 | Check for Technical Accuracy
6 | Review Phase
6.1 | Approve Editing Changes
6.2 | Meet with Editor
7 | Print Phase
7.1 | Print Proof
7.2 | Review Proof
7.3 | Print Final
8 | Book Complete

## Slide 31: Task Duration Estimates
E = Estimated Duration
M = The Most Probable Time
O = The Most Optimistic Time (5% Probability)
P = The Most Pessimistic Time (5% Probability)

## Slide 32: Units
Percentage of a resource’s time
Resource working half-time on task

## Slide 33: WBS
Task No | WBS | Task | Most Optimistic | Most Probable | Most Pessimistic | Est Duration | Task Duration
0 |  | My Training Manual |  |  |  |  | 
1 | 1 | Start Book |  |  |  |  | 
2 | 2 | Research Phase |  |  |  |  | 
3 | 2.1 | Investigate the Software | 4 | 5 | 6 | 5 | 5
4 | 2.2 | Search the Web | 1 | 1 | 1 | 1 | 1
5 | 2.3 | Interview Subject Matter Experts | 1 | 2 | 3 | 2 | 2
6 | 3 | Outline Phase |  |  |  |  | 
7 | 3.1 | Create Outline | 2 | 3 | 4 | 3 | 3
8 | 3.2 | Present to Publisher | 1 | 1 | 1 | 1 | 1
9 | 3.3 | Review with Subject Matter Expert | 1 | 1 | 1 | 1 | 1
10 | 3.4 | Revise Outline | 1 | 1 | 1 | 1 | 1
11 | 4 | Development Phase |  |  |  |  | 
12 | 4.1 | Write Lessons 1-5 | 20 | 25 | 30 | 25 | 25
13 | 4.2 | Write Lessons 6-10 | 10 | 12 | 17 | 12.5 | 12.5
14 | 4.3 | Add Graphics | 1 | 1 | 4 | 1.5 | 1.54
15 | 5 | Edit Phase |  |  |  |  | 
16 | 5.1 | Check Grammar, Spelling, and Proofread | 1 | 1 | 4 | 1.5 | 1.5
17 | 5.2 | Check for Technical Accuracy | 1 | 1 | 1 | 1 | 1
18 | 6 | Review Phase |  |  |  |  | 
19 | 6.1 | Approve Editing Changes | 1 | 1 | 1 | 1 | 1
20 | 6.2 | Meet with Editor | 1 | 1 | 1 | 1 | 1
21 | 7 | Print Phase |  |  |  |  | 
22 | 7.1 | Print Proof | 1 | 1 | 1 | 1 | 1
23 | 7.2 | Review Proof | 1 | 1 | 1 | 1 | 1
24 | 7.3 | Print Final | 1 | 1 | 1 | 1 | 1
25 | 8 | Book Complete |  |  |  |  | 

## Slide 34: Task Relationships
Finish-to-Start (FS)
Start-to-Start (SS)
Finish-to-Finish (FF)
Start-to-Finish (SF)

## Slide 35: Lesson 4 - Setting Up Resources
Set Up Resources
Enter Maximum Capacity
Entering Pay Rates
Adjusting Work Time
Setting Up Cost Resources
Documenting Resources
Student Exercise – Page 95

## Slide 36: Session I - Review
  Lesson 1 - Overview of Project Management & MS Project
  Lesson 2 - Starting a new project plan
  Lesson 3 - Building a task list
  Lesson 4 - Setting up resources

## Slide 37: Session II
Lesson 5 - Assigning resources to tasks
Lesson 6 - Formatting and sharing your plan
Lesson 7 - Tracking progress
Lesson 8 - Project Management Toolkit

## Slide 38: Lesson 5: Assigning Resources to Tasks
Assigning Resources to Tasks
Control Work Assignments
Assign Cost Resource to Tasks
Check Plan
Student Exercise – Page 120

## Slide 39: Lesson 6: Formatting and Sharing Your Plan
Customize the Gantt Chart
Add Tasks to Timeline
Customize Reports
Copy Views and Reports
Print Views and Reports
Student Exercise – Page 148

## Slide 40: Lesson 7 - Tracking Progress
Understanding Progress Tracking
Saving a Baseline Plan
Tracking a Plan As Scheduled
Entering Task Completion
Student Exercise – Page 172

## Slide 41: Lesson 8 - Project Management Toolkit

## Slide 42: Session II - Review
Lesson 5 - Assigning Resources to Tasks
Lesson 6 - Formatting and Sharing Your Plan
Lesson 7 - Tracking Progress
Lesson 8 - Project Management Toolkit

## Slide 43: MS Project 2016 - Level II
Session 1
  Lesson 1 – Advanced task scheduling
  Lesson 2 - Fine-tuning task details
  Lesson 3 - Fine-tuning resource and assignment details
  Lesson 4 - Fine-tuning the Project plan
  Lesson 5 - Organizing project details
Session 2
  Lesson 6 - Tracking progress on tasks and assignments
  Lesson 7 - Viewing and reporting project status
  Lesson 8 – Advanced formatting, printing and report formatting
  Lesson 9 – Customizing, Sharing and Consolidating Projects