## Slide 1: MS Project 2016 Level II
http://www.profburnett.com

## Slide 2: Outline
Introductions
Class Outline
Review Class Website

## Slide 3: Instructor Info
Carl Burnett
Instructor with MCC since 2007
Also teaches at JHU & CTC
Military 22 Years – Corps of Engineers
IT Contractor 20 Years (BAH, GD, Independent)
profburnett@live.com
carl.burnett@montgomerycollege.edu
240.696.1906

## Slide 4: Introductions
Name
Job
What do you to expect from course?

## Slide 5: Class Website
Class Website
Download Class Files
Bring in a Project to Manage

## Slide 6: Course Outline
Session I
  Lesson 1 – Advanced task scheduling
  Lesson 2 - Fine-tuning task details
  Lesson 3 - Fine-tuning resource and assignment details
  Lesson 4 - Fine-tuning the Project plan
  Lesson 5 - Organizing project details
Session II
  Lesson 6 - Tracking progress on tasks and assignments
  Lesson 7 - Viewing and reporting project status
  Lesson 8 – Advanced formatting, printing and report formatting
  Lesson 9 – Customizing, Sharing and Consolidating Projects

## Slide 7: Session I
  Lesson 1 – Advanced task scheduling
  Lesson 2 - Fine-tuning task details
  Lesson 3 - Fine-tuning resource and assignment details
  Lesson 4 - Fine-tuning the Project plan
  Lesson 5 - Organizing project details

## Slide 8: Lesson 1 – Advanced Task Scheduling
Task Path Relationship
Task Relationships
Task Constraints
Task Duration Types
Task Duration Calculations
Task Inspector

## Slide 9: Task Path Relationship
Predecessors
Driving Predecessors
Successors
Driving Successors

## Slide 10: Task Relationships
Finish-to-Start (FS)
Start-to-Start (SS)
Finish-to-Finish (FF)
Start-to-Finish (SF)

## Slide 11: Task Constraints

## Slide 12: Task Duration Calculations

## Slide 13: Lesson 2 - Fine-tuning Task Details
Enter deadline dates
Enter fixed costs
Create a recurring task
View the plan’s critical path
Schedule summary tasks manually

## Slide 14: Fixed Costs
Start of Task
End of Task
Prorated (Default)

## Slide 15: Lesson 3 - Fine-tuning Resource and Assignment Details
Change resource availability over multiple date ranges
Work with multiple resource pay rates
Change resource pay rates over different date ranges
Delay the start of assignments
Apply contours to assignments
Create and assign material resources
View resource capacity
Adjust assignments in the Team Planner view (Project Professional only)

## Slide 16: Assignments Contours
Flat
Back-loaded
Front-loaded
Double peak
Early peak
Late peak
Bell
Turtle

## Slide 17: Lesson 4 - Fine-tuning the Project Plan
Examine resource allocations over time
Resolve resource overallocations manually
Level overallocated resources
Check the plan’s cost and finish date
Inactivate tasks (Project Professional only)

## Slide 18: Lesson 5 - Organizing Project Details
Sort plan details
Group plan details
Filter plan details
Create new tables
Create new views

## Slide 19: Session II
Lesson 6 - Tracking progress on tasks and assignments
Lesson 7 - Viewing and reporting project status
Lesson 8 – Advanced formatting, printing and report formatting
Lesson 9 – Customizing, Sharing and Consolidating Projects

## Slide 20: Lesson 6 - Tracking Progress on Tasks and Assignments
Update a baseline
Track actual and remaining work for tasks and assignments
Track timephased actual work for tasks and assignments
Reschedule incomplete work

## Slide 21: Lesson 7 - Viewing and Reporting Project Status
Examine a plan’s variance
Identify tasks that have slipped
Examine task costs
Examine resource costs

## Slide 22: Lesson 8 – Advanced Formatting, Printing and Report Formatting
Format a Gantt chart view
Format a Timeline view
Format a Network Diagram view
Format a Calendar view
Print and export views
Create a custom report
Customize charts in a report
Customize tables in a report

## Slide 23: Lesson 9 – Customizing, Sharing and Consolidating Projects
Share custom elements between plans
Record and run macros
Edit macros
Customize the ribbon and Quick Access Toolbar
Copy Project data to and from other programs
Open files in other formats in Project
Save to other file formats from Project
Generate reports with Excel and Visio
Share a resource pool across multiple plans
Consolidate plans
Create dependencies between plans

## Slide 24: Class Evaluation
WD&CE Course Evaluation Form
http://webdb.montgomerycollege.edu/internet/wdceevals/wdceevals.cfm
Course Name: MS Project 2016 – Level II
Course CRN: 25388
Course Start Date: October 11, 2016
Course Instructor: Carl Burnett